## Sheet1
|  |  | Project Name: |  | EmployeePayrollManagement | Payroll Management
Daily Project Status Report
| team lead | arshi |  |  |  | backend lead - | ashish
|  |  | front end |  |  |  |  | Backend /Database Part
Date | name | work |  |  | Name |  | Work
2022-03-22 | arshi | Discussion On About project |  |  | Ashish |  | Discussion On About project
| ankita | Discussion On About project |  |  | Arvind |  | Discussion On About project
| anamika | Discussion On About project |  |  | Anmol |  | Discussion On About project
[5 empty] | Arnab |  | Discussion On About project
[5 empty] | Sudarshan |  | Discussion On About project
[5 empty] | Srikanth |  | Discussion On About project
|  |  | anand x | absent
2022-03-23 | arshi | discussion about design and started |  |  | Ashish |  | Discussion About Flow Chart And Database Schema
| ankita | discussion about design and started |  |  | Arvind |  | Discussion About Flow Chart And Database Schema
| anamika | discussion about design and started |  |  | Anmol |  | Discussion About Flow Chart And Database Schema
[5 empty] | Arnab |  | Discussion About Flow Chart And Database Schema
[5 empty] | Sudarshan |  | Discussion About Flow Chart And Database Schema
[5 empty] | Srikant |  | Discussion About Flow Chart And Database Schema
|  |  | anand x | absent
2022-03-24 | arshi | works on ui home /aboutus/contactus |  |  | Ashish |  | Started Doing Employee Part
| ankita | works on employee form |  |  | Arvind |  | Started doing Employee Part
| anamika | making ui of index page |  |  | Anmol |  | Started Doing Project Part
[5 empty] | Arnab |  | Started Doing Project Part
[5 empty] | Sudarshan |  | Started Doing Registration Part
[5 empty] | Srikant |  | Started Doing Registration Part
|  |  | anand x | absent
2022-03-25 | arshi | ui services /aboutus/contactus |  |  | Ashish |  | Doing Employee Part
| ankita | employee form add part |  |  | Arvind |  | doing Employee Part
| anamika | ui of index page header |  |  | Anmol |  | Doing Project Part
[5 empty] | Arnab |  | Doing Project Part
[5 empty] | Sudarshan |  | Doing Registration Part
[5 empty] | Srikant |  | Doing Registration Part
|  |  | anand x | absent
2022-03-26 | arshi | works on project module connection |  |  | Ashish |  | Working On Backend Errors
| ankita | works on curd operation in employee module | connection |  | Arvind |  | Working On Backend Errors
| anamika | works on registrastion | connection |  | Anmol |  | Working On Backend Errors
[5 empty] | Arnab |  | Working On Backend Errors
[5 empty] | Sudarshan |  | Working On Backend Errors
[5 empty] | Srikant |  | Working On Backend Errors
|  |  | anand x | absent
2022-03-27 | arshi | works on connection |  |  | Ashish |  | connection with ui
| ankita | works on curd /view /update |  |  | Arvind |  | connection with ui
| anamika | works on connection |  |  | Anmol |  | connection with ui
[5 empty] | Arnab |  | connection with ui
[5 empty] | Sudarshan |  | connection with ui
[5 empty] | Srikant |  | connection with ui
|  |  | anand x | absent
2022-03-28 | arshi | adding more ui pages |  |  | Ashish |  | Post Man Execution
| ankita | works on curd / delete |  |  | Arvind |  | Post Man Execution
| anamika | fixing ui index page |  |  | Anmol |  | Post Man Execution
[5 empty] | Arnab |  | Post Man Execution
[5 empty] | Sudarshan |  | Post Man Execution
[5 empty] | Srikant |  | Post Man Execution

## Sheet2
Project Name- employee payroll management
Group Number - 2
Team Lead & Frontend Lead- arshi
Backend Lead - ashish

## Sheet3
Status Meeting Group - 2 / Epayroll
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2020-02-23 | 9:30 | a | 2:30 | a | 6:00 | a
2020-02-24 | 9:30 | a | 1:00 | a | 6:30 | a
2020-02-25 | 9:30 | a | 2:00 | a | 6:20 | a
2020-02-26 | 9:30 | a | 2:00 | a | 6:30 | a
2020-02-27 | 9:30 | a | 1:30 | a | 7:00 | a
2020-02-28 | 10:30 | a | 2:30 | a | 6:30 | a